## XIB
Version No:1.0 / Last Updated Date:14-Aug-18

Project Name: MISHOP iOS App
Client Name: Wayne

Sr. No	Tasks	Estimated				Actual				Task to be done by	Status	Comments
		Start Date	End Date	In Day(s)	In Hour(s)	Start Date	End Date	In Day(s)	In Hour(s)

1	SideBar - WithOut Login				0					Hardik Vyas	Scheduled
2	SideBar - With Login				0					Hardik Vyas	Scheduled
3	SignUp	2 Aug 18	2 Aug 18		2	2 Aug 18	2 Aug 18		2	Hardik Vyas	Testing
4	Login	2 Aug 18	2 Aug 18		2	2 Aug 18	2 Aug 18		2	Hardik Vyas	Testing
5	About Us	2 Aug 18	2 Aug 18		1	2 Aug 18	2 Aug 18		1	Hardik Vyas	Testing
6	Contact Us	2 Aug 18	2 Aug 18		2	2 Aug 18	2 Aug 18		2	Hardik Vyas	Testing
7	My Profile	14 Aug 18	16 Aug 18		8	17 Aug 18	17 Aug 18		5	Kinjal Gadhia	Testing
7.1	Follower List	16 Aug 18	16 Aug 18		2	17 Aug 18	17 Aug 18		1	Kinjal Gadhia	Testing
7.2	Following List	16 Aug 18	16 Aug 18		2	17 Aug 18	17 Aug 18		1	Kinjal Gadhia	Testing
8	Edit Profile	17 Aug 18	17 Aug 18		4	17 Aug 18	18 Aug 18		2	Kinjal Gadhia	Testing
9	Splash Screen	2 Aug 18	2 Aug 18		1					Hardik Vyas	Testing
10	Account Setting	3 Aug 18	3 Aug 18		1	2 Aug 18	3 Aug 18		1	Hardik Vyas	Testing
10.1	Email Setting	3 Aug 18	3 Aug 18		1.5	3 Aug 18	3 Aug 18		1.5	Hardik Vyas	Testing
10.2	Change Password	3 Aug 18	3 Aug 18		1.5	3 Aug 18	3 Aug 18		1.5	Hardik Vyas	Testing
10.3	My Shipping Address	3 Aug 18	3 Aug 18		1.5	3 Aug 18	3 Aug 18		1.5	Hardik Vyas	Testing
11	Discount Store	3 Aug 18	3 Aug 18		2.5	17 Aug 18	18 Aug 18		2.5	Hardik Vyas	Testing
12	Product Listing with Filter Dialog	4 Aug 18	4 Aug 18		2	18 Aug 18	20 Aug 18		2	Hardik Vyas	Testing
13	Orders					Hardik Vyas
13.1	My Balance	4 Aug 18	4 Aug 18		4.5	6 Aug 18	6 Aug 18		5	Hardik Vyas	Testing
13.2	Purchase History	4 Aug 18	6 Aug 18		3	6 Aug 18	7 Aug 18		3	Hardik Vyas	Testing
13.3	Sale History	6 Aug 18	6 Aug 18		3	7 Aug 18	7 Aug 18		3	Hardik Vyas	Testing
15	Add Party	6 Aug 18	7 Aug 18		5	20 Aug 18	20 Aug 18		5	Hardik Vyas	Testing
16	Add Product	7 Aug 18	14 Aug 18		8	20 Aug 18	21 Aug 18		6	Hardik Vyas	Running
17	Product Details	14 Aug 18	14 Aug 18		6	15 Aug 18	15 Aug 18		5	Kinjal Gadhia	Testing
18	Bids List	14 Aug 18	16 Aug 18		2.5	17 Aug 18	17 Aug 18		1	Kinjal Gadhia	Testing
19	Favourites List	16 Aug 18	16 Aug 18		2.5	14 Aug 18	14 Aug 18		2.5	Hardik Vyas	Testing
20	Feeds	16 Aug 18	16 Aug 18		2.5	14 Aug 18	16 Aug 18		2.5	Hardik Vyas	Testing
21	Home	16 Aug 18	17 Aug 18		2.5	16 Aug 18	17 Aug 18		2.5	Hardik Vyas	Testing
22	Likes	17 Aug 18	17 Aug 18		2.5	17 Aug 18	17 Aug 18		2.5	Hardik Vyas	Testing
23	Messages					Hardik Vyas
23.1	Inbox	17 Aug 18	17 Aug 18		2	4 Aug 18	4 Aug 18		2	Hardik Vyas	Testing
23.2	Sent	17 Aug 18	17 Aug 18		2	4 Aug 18	4 Aug 18		2	Hardik Vyas	Testing
23.3	Deleted	18 Aug 18	18 Aug 18		1	4 Aug 18	4 Aug 18		1	Hardik Vyas	Testing
23.4	Message Detail	18 Aug 18	18 Aug 18		2.5	4 Aug 18	4 Aug 18		3	Hardik Vyas	Testing
23.4	Message Forward	18 Aug 18	18 Aug 18		1	6 Aug 18	6 Aug 18		1	Hardik Vyas	Testing
23.5	Message Reply	18 Aug 18	18 Aug 18		1	6 Aug 18	6 Aug 18		1	Hardik Vyas	Testing
24	News	18 Aug 18	20 Aug 18		3	17 Aug 18	17 Aug 18		3.5	Hardik Vyas	Testing
25	Parties List	17 Aug 18	17 Aug 18		3	18 Aug 18	18 Aug 18		1.5	Kinjal Gadhia	Testing
26	Shopping Cart	20 Aug 18	20 Aug 18		5					Hardik Vyas	Scheduled
27	Shops	20 Aug 18	20 Aug 18		2.5					Hardik Vyas	Scheduled
27.1	Message Send	21 Aug 18	21 Aug 18		1					Hardik Vyas	Scheduled
27.1	Party Details	17 Aug 18	18 Aug 18		6	18 Aug 18	18 Aug 18		3	Kinjal Gadhia	Testing
28	Send Party Invitation	18 Aug 18	18 Aug 18		2	18 Aug 18	18 Aug 18		1	Kinjal Gadhia	Testing
29	Add Party Products	18 Aug 18	20 Aug 18		2	18 Aug 18	18 Aug 18		2	Kinjal Gadhia	Testing
30	Request Bundle	20 Aug 18	20 Aug 18		2	18 Aug 18	20 Aug 18		2	Kinjal Gadhia	Testing
31	Create Bundle	20 Aug 18	20 Aug 18		3	20 Aug 18	20 Aug 18		4.5	Kinjal Gadhia	Testing
32	My Parties	20 Aug 18	21 Aug 18		2.5	20 Aug 18	21 Aug 18		2.5	Kinjal Gadhia	Testing
33	View Bundle Detail	21 Aug 18	21 Aug 18		2.5	21 Aug 18	21 Aug 18		2.5	Kinjal Gadhia	Testing

				0	120			0	96.5
	Total Time			15				12.0625

Project Start Date: 2-Aug-2018
Project Delivery Date: 21-Aug-2018

## Development
Version No:1.0 / Last Updated Date:14-Aug-18

Project Name: MISHOP iOS App
Client Name: Wayne

Sr. No	Tasks	Estimated				Actual				Task to be done by	Status	Comments
		Start Date	End Date	In Day(s)	In Hour(s)	Start Date	End Date	In Day(s)	In Hour(s)

1	Design Implementation	2 Aug 18	21 Aug 18	16		2 Aug 18				Hardik Vyas	Scheduled

2	Default Classes Setup	22 Aug 18	22 Aug 18		5	1 Aug 18	1 Aug 18		5	Hardik Vyas	Testing

3	API Calling Classes Setup	22 Aug 18	23 Aug 18		4	1 Aug 18			3	Hardik Vyas	Running

4	Push Notification Setup & Manage	23 Aug 18	24 Aug 18		5					Hardik Vyas	Scheduled

5	Navigation Drawer Setup	24 Aug 18	27 Aug 18	1		3 Aug 18			2	Hardik Vyas	Running

6	Multi Currency Setup And Selection	27 Aug 18	27 Aug 18		3					Hardik Vyas	Scheduled

7	Login View
7.1	Login Api	21 Aug 18	21 Aug 18		2	22 Aug 18	22 Aug 18		2	Kinjal Gadhia	Testing
7.2	forgot password	21 Aug 18	21 Aug 18		1	22 Aug 18	22 Aug 18		1	Kinjal Gadhia	Testing
7.3	Login with Facebook	21 Aug 18	21 Aug 18		1	22 Aug 18	22 Aug 18		1	Kinjal Gadhia	Testing

8	Sign Up
8.1	Signup Api calling With validation	22 Aug 18	22 Aug 18		2	22 Aug 18	22 Aug 18		2	Kinjal Gadhia	Testing
8.2	Login with Facebook	22 Aug 18	22 Aug 18		1	22 Aug 18	22 Aug 18		1	Kinjal Gadhia	Testing

9	My Shop (User Profile)
9.1	Get My Profile Details	22 Aug 18	22 Aug 18		2	22 Aug 18	24 Aug 18		2	Kinjal Gadhia	Testing
9.2	Get My Product List	22 Aug 18	22 Aug 18		2					Kinjal Gadhia	Scheduled
9.3	Delete My product	22 Aug 18	22 Aug 18		1	23 Aug 18	23 Aug 18		1	Kinjal Gadhia	Testing
9.4	Report User	23 Aug 18	23 Aug 18		1					Kinjal Gadhia	Scheduled
9.5	Send Message	23 Aug 18	23 Aug 18		2					Kinjal Gadhia	Scheduled
9.6	Follow/Unfollow Owner	23 Aug 18	23 Aug 18		1	23 Aug 18	23 Aug 18		1	Kinjal Gadhia	Testing

10	Follower
10.1	Get follower list	23 Aug 18	23 Aug 18		2	23 Aug 18	24 Aug 18		2	Kinjal Gadhia	Testing
10.2	Follow/Unfollow api	23 Aug 18	23 Aug 18		1					Kinjal Gadhia	Scheduled

11	Following
11.1	Get following list	23 Aug 18	24 Aug 18		2	24 Aug 18	24 Aug 18		2	Kinjal Gadhia	Testing
11.2	Follow/Unfollow api	24 Aug 18	24 Aug 18		1	24 Aug 18	24 Aug 18		1	Kinjal Gadhia	Testing

12	Edit Profile Details
12.1	Get My Profile Details api	24 Aug 18	24 Aug 18		2	24 Aug 18	24 Aug 18		2	Kinjal Gadhia	Testing
12.2	Get Country Api	24 Aug 18	24 Aug 18		1	24 Aug 18	24 Aug 18		1	Kinjal Gadhia	Testing
12.3	Get State Api	24 Aug 18	24 Aug 18		1	24 Aug 18	24 Aug 18		1	Kinjal Gadhia	Testing
12.4	Get City Api	24 Aug 18	24 Aug 18		1	24 Aug 18	24 Aug 18		0.5	Kinjal Gadhia	Testing
12.5	Update Profile	24 Aug 18	27 Aug 18		2	27 Aug 18	27 Aug 18		2	Kinjal Gadhia	Testing

13	Products
13.1	Get Product List Api	27 Aug 18	27 Aug 18		3					Hardik Vyas	Scheduled
13.2	Search Product	27 Aug 18	27 Aug 18		2					Hardik Vyas	Scheduled
13.3	Delete My product	27 Aug 18	27 Aug 18		1					Hardik Vyas	Scheduled

14	Filter For Product
14.1	Get Category	27 Aug 18	27 Aug 18		1					Hardik Vyas	Scheduled
14.2	Get Availability	27 Aug 18	27 Aug 18		1					Hardik Vyas	Scheduled
14.3	Get Condition	28 Aug 18	28 Aug 18		1					Hardik Vyas	Scheduled
14.4	Get Auction	28 Aug 18	28 Aug 18		1					Hardik Vyas	Scheduled
14.5	Apply Filter	28 Aug 18	28 Aug 18		2					Hardik Vyas	Scheduled

15	Home
15.1	Get Shop List	28 Aug 18	28 Aug 18		3					Hardik Vyas	Scheduled

16	Shops
16.1	Get Shop List	28 Aug 18	29 Aug 18		3					Hardik Vyas	Scheduled
16.2	Search Shop	29 Aug 18	29 Aug 18		2					Hardik Vyas	Scheduled
16.3	Shop Filter By Location	29 Aug 18	29 Aug 18		2					Hardik Vyas	Scheduled

17	Feeds
17.1	Get Feed List	29 Aug 18	29 Aug 18		2					Hardik Vyas	Scheduled
17.2	Search Feed	30 Aug 18	30 Aug 18		2					Hardik Vyas	Scheduled

18	News
18.1	Get News Listing	30 Aug 18	30 Aug 18		2					Hardik Vyas	Scheduled
18.2	News Redirection	30 Aug 18	30 Aug 18		1					Hardik Vyas	Scheduled

19	Discount Store
19.1	Get Discount Store Listing	30 Aug 18	30 Aug 18		2					Hardik Vyas	Scheduled
19.2	Search Discount Listing	30 Aug 18	31 Aug 18		2					Hardik Vyas	Scheduled

20	Bids
20.1	Get Bids Listing	27 Aug 18	27 Aug 18		3	27 Aug 18	27 Aug 18	2		Kinjal Gadhia	Scheduled

21	Likes
21.1	Get Like Product Listing	27 Aug 18	27 Aug 18		2					Kinjal Gadhia	Scheduled
21.2	Unlike Product	27 Aug 18	27 Aug 18		1					Kinjal Gadhia	Scheduled
21.3	Search Like Product	27 Aug 18	28 Aug 18		2					Kinjal Gadhia	Scheduled

22	Favourite
22.1	Get Favourite Product Listing	28 Aug 18	28 Aug 18		2					Kinjal Gadhia	Scheduled
22.2	Remove Favourite Product	28 Aug 18	28 Aug 18		1					Kinjal Gadhia	Scheduled
22.3	Search Favourite Product	28 Aug 18	28 Aug 18		2					Kinjal Gadhia	Scheduled

23	Order
23.1	My balance
23.1.1	Get Mybalance	31 Aug 18	31 Aug 18		1					Hardik Vyas	Scheduled
23.1.2	Get Redemption history list	31 Aug 18	31 Aug 18		2					Hardik Vyas	Scheduled
23.1.3	Send Redemption Request	31 Aug 18	31 Aug 18		1					Hardik Vyas	Scheduled
23.2	Purchase History
23.2.1	Get Purchase History Api	31 Aug 18	31 Aug 18		3					Hardik Vyas	Scheduled
23.3	Sale History
23.3.1	Get Sale History Api	5 Sep 18	5 Sep 18		3					Hardik Vyas	Scheduled

24	Parties
24.1	Get Parties List	28 Aug 18	29 Aug 18		3					Kinjal Gadhia	Scheduled
24.2	Search Parties List	29 Aug 18	29 Aug 18		2					Kinjal Gadhia	Scheduled

25	My Parties
25.1	Get My parties list	29 Aug 18	29 Aug 18		2					Kinjal Gadhia	Scheduled
25.2	Delete my Parties	29 Aug 18	29 Aug 18		1					Kinjal Gadhia	Scheduled

26	Party Detail
26.1	Get Party Details	29 Aug 18	30 Aug 18		4					Kinjal Gadhia	Scheduled

27	Invite Host
27.1	Get Host List	5 Sep 18	5 Sep 18		2					Hardik Vyas	Scheduled
27.2	Invite host api	5 Sep 18	5 Sep 18		1					Hardik Vyas	Scheduled

28	Add Product In party
28.1	Get Product List Api	30 Aug 18	30 Aug 18		2					Kinjal Gadhia	Scheduled
28.2	Add Product In party api	30 Aug 18	30 Aug 18		2					Kinjal Gadhia	Scheduled

29	Add Product
29.1	Get Product Types list	30 Aug 18	31 Aug 18		3	27 Aug 18	27 Aug 18		3	Kinjal Gadhia	Testing
29.2	Get Size List	31 Aug 18	31 Aug 18		3	27 Aug 18				Kinjal Gadhia	Running
29.3	Submit Product	31 Aug 18	31 Aug 18		2					Kinjal Gadhia	Scheduled

30	Edit Product
30.1	Get Product Details	31 Aug 18	31 Aug 18		2					Kinjal Gadhia	Scheduled
30.2	Set Product Details	1 Sep 18	1 Sep 18		2					Kinjal Gadhia	Scheduled
30.3	Submit Product	1 Sep 18	1 Sep 18		2					Kinjal Gadhia	Scheduled

31	Product Details
31.1	Get Product Details	5 Sep 18	6 Sep 18		3					Hardik Vyas	Scheduled
31.2	Like product	6 Sep 18	6 Sep 18		1					Hardik Vyas	Scheduled
31.3	Share product	6 Sep 18	6 Sep 18		2					Hardik Vyas	Scheduled
31.4	Report Product	6 Sep 18	6 Sep 18		1					Hardik Vyas	Scheduled
31.5	Get Comment	6 Sep 18	6 Sep 18		2					Hardik Vyas	Scheduled
31.6	Add Comment	6 Sep 18	7 Sep 18		2					Hardik Vyas	Scheduled
31.7	Add to cart	7 Sep 18	7 Sep 18		1					Hardik Vyas	Scheduled
31.8	Bid Now	7 Sep 18	7 Sep 18		2					Hardik Vyas	Scheduled

32	View Bids
32.1	Get View bids of product	7 Sep 18	7 Sep 18		3					Hardik Vyas	Scheduled

33	Add New Party
33.1	Get Party Categories	1 Sep 18	1 Sep 18		2					Kinjal Gadhia	Scheduled
33.2	Submit Party Details	1 Sep 18	1 Sep 18		2					Kinjal Gadhia	Scheduled

34	Account Setting
34.1	Change Password
34.1.1	Update Password API	7 Sep 18	10 Sep 18		2					Hardik Vyas	Scheduled
34.2	Email Setting
34.2.1	Get Email Settings	10 Sep 18	10 Sep 18		1					Hardik Vyas	Scheduled
34.2.2	Save Email Settings	10 Sep 18	10 Sep 18		1					Hardik Vyas	Scheduled
34.3	My Shipping Address
34.3.1	Get My Shipping Address	10 Sep 18	10 Sep 18		1					Hardik Vyas	Scheduled
34.3.2	Get Country Api	10 Sep 18	10 Sep 18		1					Hardik Vyas	Scheduled
34.3.3	Get State Api	10 Sep 18	10 Sep 18		1					Hardik Vyas	Scheduled
34.3.4	Get City Api	10 Sep 18	10 Sep 18		1					Hardik Vyas	Scheduled
34.3.5	Save Address	10 Sep 18	10 Sep 18		1					Hardik Vyas	Scheduled

35	Messages
35.1	Inbox
35.1.1	Get Inbox Messages	11 Sep 18	11 Sep 18		3					Hardik Vyas	Scheduled
35.1.2	Delete Inbox Message	11 Sep 18	11 Sep 18		1					Hardik Vyas	Scheduled
35.2	Sent
35.2.1	Get Sent Messages	11 Sep 18	11 Sep 18		2					Hardik Vyas	Scheduled
35.2.2	Delete Sent Message	11 Sep 18	11 Sep 18		1					Hardik Vyas	Scheduled
35.3	Deleted
35.3.1	Get Deleted Messages	11 Sep 18	12 Sep 18		2					Hardik Vyas	Scheduled
35.3.2	Delete Deleted Message	12 Sep 18	12 Sep 18		1					Hardik Vyas	Scheduled

36	Message Details
36.1	Get Message Details	12 Sep 18	12 Sep 18		3					Hardik Vyas	Scheduled
36.2	Reply Message	12 Sep 18	12 Sep 18		1					Hardik Vyas	Scheduled
36.3	Forward Message	12 Sep 18	12 Sep 18		1					Hardik Vyas	Scheduled

37	Shopping Cart
37.1	Get cart Details	10 Sep 18	10 Sep 18		3					Kinjal Gadhia	Scheduled
37.2	Remove product from cart	10 Sep 18	10 Sep 18		1					Kinjal Gadhia	Scheduled
37.3	Check for quantity	10 Sep 18	10 Sep 18		2					Kinjal Gadhia	Scheduled

38	Paypal Checkout Using Web-view	10 Sep 18	10 Sep 18		2					Kinjal Gadhia	Scheduled

39	Request Bundle
39.1	Get Product List Api	11 Sep 18	11 Sep 18		2					Kinjal Gadhia	Scheduled
39.2	Send Bundle Request	11 Sep 18	11 Sep 18		2					Kinjal Gadhia	Scheduled

40	Create Bundle
40.1	Get bundle details	11 Sep 18	11 Sep 18		2					Kinjal Gadhia	Scheduled
40.2	Create Bundle Api	11 Sep 18	11 Sep 18		2					Kinjal Gadhia	Scheduled

41	Bundle Details
41.1	Get bundle Details Api	12 Sep 18	12 Sep 18		4					Kinjal Gadhia	Scheduled
41.2	Buy now bundle	12 Sep 18	12 Sep 18		1					Kinjal Gadhia	Scheduled

42	About Us	12 Sep 18	12 Sep 18		1					Kinjal Gadhia	Scheduled

43	Contact Us	12 Sep 18	12 Sep 18		2					Kinjal Gadhia	Scheduled

44	Logout	13 Sep 18	13 Sep 18		1					Kinjal Gadhia	Scheduled

45	Splash screen And App Icon	13 Sep 18	13 Sep 18		1					Kinjal Gadhia	Scheduled
46	Auto login	13 Sep 18	13 Sep 18		1					Kinjal Gadhia	Scheduled
47	Testing	14 Sep 18	24 Sep 18	8	0					Lipi	Scheduled

				25	207			2	32.5
	Total Time			50.875				6.0625

Project Start Date: 2-Aug-2018
Project Delivery Date: 24-Sept-2018